## Timeline
Roles Representation
Frontend Developer | Rory
Backend Developer | Ronan
Buseness Analyst / Test Analyst | Kasia
Project Manager / Tesy Analyst | Geneci
Dates | 2020-10-11 | 2020-10-18 | 2020-10-25 | 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-14
Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Analysis | bar: W1
Design | bar: W2 to W4
Development
Sprint 1 | bar: W5 to W7
QA Test | W6: Test Cases; W7: Testing
Sprint 2 | bar: W6 to W8
E2E QA | W7: Test Cases; W8: Testing
E2E UAT | W9: UAT Test
Deployement | bar: W10
Go Live
Video Presentation

## ProjectLogs
Date | What | Who | Status | Obsergvation | Next Step | Allocated hours
Project Log
2020-10-11 | First project meeting on Skype Decision was made on: * Team Representation Roles * Web Shop topic * Project timeline * Tools to Code Version control - GitHub | Geneci - x19175108 Kasia - x19176414 Ronan - x19141815 Rory - x19139306 | Done | We decided on taking a mixture of Agile RAD approach | Group member to draft project proposal and email each other by Friday 16/10/2020. Team to join again on Skype Saturday 17/10/2020 to gather content and organize document to submit. | 1.5
2020-10-18 | Workshop on how to use GitHub - Rory to the group Review Proposal contents Review Mockups Decision on having a Developer responsible for FrontEnd(Rory) Decision oh having a person responsible for Backend development(Ronan) Decision was made to have a person responsible for FrontEnd Testing(Kasia) Decision to have a person responsible for Backend Testing(Geneci) Decison to email Liam regarding document size. | Rory - x19139306 Ronan - x19141815 Kasia - x19176414 Geneci - x19175108 | Geneci to review document format Ronan to fix some mockups page based on discussion |  | Design User Case and Sequence Diagrams Start List of all frontend fields based on mockups List of possibles entintes based on mockups and requeirements lists Research on Color schemes Design logo and header Design footer List of information to appear on footer Next meeting 25/10/2020 | 1.5
2020-10-26 | Working on Logo proposal Working on Colour scheme | Rory - x19139306 Ronan - x19141815 Kasia - x19176414 Geneci - x19175108 | Kasia and Rory to start working on HTML and CSS based on decision for Logo and Colour Scheme Geneci and Ronan to start working on Database relationship based on information from the Mockups | Decision on colour scheme and logo was made based on it is necessary to be there. | Next meeting 01/11/2020. Time TBC Kasia and Rory to present progress on Frontend Geneci and Ronan to present progress on Backend | 1.5
2020-11-01 | Analysis and discussion on class diagram Customer side relationship Product side relationship | Rory - x19139306 Ronan - x19141815 Kasia - x19176414 Geneci - x19175108 | Presentation on work done for the backend | Decision was made ot keep the database as simple as wecould to allow us to have a full working web application. Tables for database is based on excel file Customer_Tables and Products_Tables uploaded to Github today. | Ronan /Geneci to work in a full class diagram for the application Rory / Kasia to work on sample code for the frontend and logo | 1.5
2020-11-07 | Discussion on Class diagram | Ronan - x19141815 Geneci - x19175108 | Entire Class Diagram analysis | Ronan organized in one unique class diagram the proposal discussed last week with team We met today to adjust the class diagram and it was agreed to delete the CartItem and make it to the Shopping Cart | Ronan to upload the class diagram to Github for analysis by the team and further suggestion | 3
2020-11-07 | Discussion on FrontEnd | Rory - x19139306 Kasia - x19176414
2020-11-14 | Working on FrontEnd | Rory - x19139306 Kasia - x19176414
2020-11-14 | Creating database relationship workbench | Geneci - x19175108 Ronan - x19141815 | Database tables and relationship created | All tables ere created. Relationship to be tested with data | Enter some data to test the relationship. Start creating tables in test enviroment | 3
2020-11-21 | User authentication functionality in test enviroment | Ronan - x19141815 Geneci - x19175108
2020-11-22 | Assignment tasks for Technical Functionalities delivery | Geneci - x19175108 Kasia - x19176414 Rory - x19139306 Ronan - x19141815 | In progress | Discussion on what is need for technical specification. Adjustment on Proposal to Technical Specification | Ronan to work on Model / database specification Kasia to design to User Flow Rory to provide FrontEnd technical specification Geneci to provide backend technical specification | 1