## Timeline
Roles Representation
Frontend Developer | Rory
Backend Developer | Ronan
Buseness Analyst / Test Analyst | Kasia
Project Manager / Tesy Analyst | Geneci
Dates | 2020-10-11 | 2020-10-18 | 2020-10-25 | 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-14
Project Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Analysis | bar: W1
Design | bar: W2 to W3
Development
Sprint 1 | bar: W4 to W5
QA Test | W5: Test Cases; W6: Testing
Sprint 2 | bar: W6 to W7
E2E QA | W7: Test Cases; W8: Testing
E2E UAT | W9: UAT Test
Deployement | bar: W10
Go Live
Video Presentation

## ProjectLogs
Project Log
Date | What | Who | Status | Obsergvation | Next Step
2020-10-11 | First project meeting on Skype Decision was made on: * Team Representation Roles * Web Shop topic * Project timeline * Tools to Code Version control - GitHub | Geneci - x19175108 Kasia - x19176414 Ronan - x19141815 Rory - x19139306 | Done | We decided on taking a mixture of Agile RAD approach | Group member to draft project proposal and email each other by Friday 16/10/2020. Team to join again on Skype Saturday 17/10/2020 to gather content and organize document to submit.
2020-10-18 | Workshop on how to use GitHub - Rory to the group Review Proposal contents Review Mockups Decision on having a Developer responsible for FrontEnd(Rory) Decision oh having a person responsible for Backend development(Ronan) Decision was made to have a person responsible for FrontEnd Testing(Kasia) Decision to have a person responsible for Backend Testing(Geneci) Decison to email Liam regarding document size. | Rory - x19139306 Ronan - x19141815 Kasia - x19176414 Geneci - x19175108 | Geneci to review document format Ronan to fix some mockups page based on discussion |  | Design User Case and Sequence Diagrams Start List of all frontend fields based on mockups List of possibles entintes based on mockups and requeirements lists Research on Color schemes Design logo and header Design footer List of information to appear on footer Next meeting 25/10/2020